## Complete
WBS | Task | Task Lead | Status | Start | End | Duration (Days) | % Complete | Working Days | Days Complete | Days Remaining | 2015-08-31 | 2015-09-07 | 2015-09-14 | 2015-09-21 | 2015-09-28 | 2015-10-05 | 2015-10-12 | 2015-10-19 | 2015-10-26 | 2015-11-02 | 2015-11-09 | 2015-11-16 | 2015-11-23 | 2015-11-30 | 2015-12-07
1 | Task Category 1
1.1 | SOW Problem Statement Rough Draft | Ernest | Finished | 2015-09-04 | 2015-09-10 | 6 | 100% | 5 | 5 | 1
SOW Problem Statement Rough Draft Delivery
1.2 | SOW Objectives and Introduction Rough Draft | Raghav | Finished | 2015-09-12 | 2015-09-16 | 4 | 100% | 3 | 3 | 1
SOW Objectives and Introduction Rough Draft Delivery
12 | SOW 0.1 | Sarthak | Finished | 2015-09-04 | 2015-09-19 | 15 | 100% | 14 | 13 | 2
SOW 0.1 Delivery
1.3 | SOW Solution, Resources, and Schedule Rough Draft | Lovissa | Finished | 2015-11-01 | 2015-11-06 | 5 | 100% | 4 | 3 | 2
SOW Solution, Resources, and Schedule Rough Draft Delivery
1.4 | SOW 1.0 | Ernest | Finished | 2015-09-04 | 2015-11-15 | 71 | 100% | 70 | 67 | 4
SOW 1.0 Delivery
2 | Task Category 2
2.1 | FR Alternatives and Criteria Rough Draft | Ernest | Finished | 2015-09-27 | 2015-09-30 | 3 | 100% | 3 | 3 | 0
FR Alternatives and Criteria Rough Draft Delivery
2.2 | FR Methods Rough Draft | Jeongsoo | Finished | 2015-10-05 | 2015-10-09 | 4 | 100% | 4 | 3 | 1
FR Methods Rough Draft Delivery
2.3 | FR Methods Intro/Conclusion/Recommendations Rough Draft | Raghav | Finished | 2015-10-09 | 2015-10-16 | 7 | 100% | 6 | 5 | 2
FR Methods intro/Conclusion/Recommendations Rough Draft Delivery
2.4 | FR 0.1 | Sarthak | Finished | 2015-10-14 | 2015-10-17 | 3 | 100% | 3 | 3 | 0
FR 0.1 Delivery
2.5 | FR 1.0 | Jeongsoo | Finished | 2015-10-28 | 2015-11-01 | 3 | 100% | 3 | 3 | 0
FR 1.0 Delivery
3 | Task Category 3
Final Presentation
4 | Task Category 4
4.1 | Final Presentation PPT Rough Draft | Raghav | Finished | 2015-11-16 | 2015-11-20 | 4 | 100% | 3 | 3 | 1
Final Presentation PPT Rough Draft Delivery
4.1 | Final Presentation PPT | Sarthak | In Progress | 2015-11-16 | 2015-12-11 | 25 | 65% | 23
Final Presentation PPT Delivery
4.2 | Data Visualization Prototype | Raghav | Finished | 2015-09-29 | 2015-11-19 | 60 | 100% | 50 | 55 | 5
0 | Data Visualization Prototype Delivery
5 | Task Category 5
5.1 | Status Report 5 | Raghav | Finished | 2015-09-24 | 2015-09-25 | 1 | 100% | 1 | 1 | 0
Status Report 5 Delivery
5.1 | Status Report 6 | Sarthak | Finished | 2015-10-01 | 2015-10-02 | 1 | 100% | 1 | 1 | 0
Status Report 6 Delivery
5.1 | Status Report 7 | Ernest | Finished | 2015-10-08 | 2015-10-09 | 1 | 100% | 1 | 1 | 0
Status Report 7 Delivery
5.1 | Status Report 8 | Lovissa | Finished | 2015-10-15 | 2015-10-16 | 1 | 100% | 1 | 1 | 0
Status Report 8 Delivery
5.1 | Status Report 9 | Ernest | Finished | 2015-10-22 | 2015-10-23 | 1 | 100% | 1 | 1 | 0
Status Report 9 Delivery
5.1 | Status Report 10 | Raghav | Finished | 2015-10-30 | 2015-10-31 | 1 | 100% | 1 | 1 | 0
Status Report 10 Delivery
5.1 | Status Report 11 | Sarthak | Finished | 2015-11-05 | 2015-11-06 | 1 | 100% | 1 | 1 | 0
Status Report 11 Delivery
5.1 | Status Report 12 | Jeongsoo | Finished | 2015-11-12 | 2015-11-13 | 1 | 100% | 1 | 1 | 0
Status Report 12 Delivery
5.1 | Final Status Report | Lovissa | Finished | 2015-11-19 | 2015-11-20 | 1 | 100% | 1 | 1 | 0
Final Status Report Delivery
5.2 | WBS Draft 1 | Jeongsoo | Finished | 2015-09-15 | 2015-09-18 | 3 | 100% | 2 | 2 | 1
WBS Draft 1 Delivery
5.2 | WBS Draft 2 | Lovissa | Finished | 2015-11-16 | 2015-11-17 | 1 | 100% | 1 | 1 | 0
WBS Draft 2 Delivery
5.2 | Final WBS | Jeongsoo | Not Start | 2015-09-15 | 2015-11-29 | 73 | 100% | 73 | 73 | 0
Final WBS Delivery
5.3 | Gantt Chart Draft 1 | Raghav | Finished | 2015-09-15 | 2015-09-18 | 3 | 100% | 2 | 2 | 1
Gantt Chart Draft 1 Delivery
5.3 | Gantt Chart Draft 2 | Sarthak | Finished | 2015-11-16 | 2015-11-17 | 1 | 100% | 1 | 1 | 0
Gantt Chart Draft 2 Delivery
5.3 | Final Gantt Chart | Sarthak | Not Start | 2015-09-15 | 2015-11-29 | 73 | 100% | 73 | 73 | 0
Final Gantt Chart Delivery